## Sheet1
Summary of actions | Action description | Priority (1 = short term, 2 = medium-term, 3 = longer-term) | End date | Oversight | Implementation partners | BRE lead workstream | Existing resources available | Additional resources required | Risks | Risk mitigation
1. Increase contribution of PSNP shock response to prevention of malnutrition through adjustments in design & implementation | The PSNP Transfers Technical Committee oversees process of considering how the PSNP shock response can maximise its contribution to the prevention of malnutrition resulting from shocks through improved timeliness, targeting & adjustments in resource transfer value, quality and modalities. |  | end 2023 | PSNP Transfers Technical Committee |  | Scalable Safety Nets | within existing planned budgets | No
1.1. Focus on improving the timeliness of resource transfers | As already planned in PSNP5 shock response design focus on (1) drought risk financing to ensure resources are available in advance (2) preparedness planning, (3) strengthening Early Warning System | 1 | as per exisitig PSNP5 plans | PSNP Transfers Technical Committee | as per existing plans | Scalable Safety Nets
1.2. Adjust PSNP targeting to take account of nutrition vulnerability | Within guidance and training of kebele selection committees ensure focus on nutrition vulnerability in selection of recipient households. | 1 | mid 2022 | PSNP Transfers Technical Committee | PSNP Transfers Technical Committee | Scalable Safety Nets
| Operational research: Using historical data, undertake a mapping of rates of malnutrition, extreme poverty, exposure to drought and PSNP shock response coverage to better understand the correlations between these three factors and extent to which the PSNP shock response targets areas most at risk of malnutrition and whether targeting might be modified in subsequent phases to strengthen a malnutrition prevention role. | 2 | end 2022 | PSNP Transfers Technical Committee | MoA FSCD, MoH, EPHI, World Bank, FEWSnet | Scalable Safety Nets
| Consider geographical re-targeting of the Core PSNP-5 following mid-term review at woredas where risk of malnutrition resulting from shocks is high (NB. not only drought or food security related) | 3 | end 2023 | PSNP Transfers Technical Committee | PSNP Transfers Technical Committee | Scalable Safety Nets
1.3. Explore opportunities for increasing the value, quality & flexibility of resource transfers | Clarify the plan for integrating HFA into the PSNP & explore opportunities to increase the value of cash transfers in order to improve the quality of the diet and meet non-food as well as food needs. | 1 | mid 2022 | PSNP Transfers Technical Committee | MoA FSCD, NDRMC | Scalable Safety Nets
| Undertake a mapping of the type and quality of resource transfers provided through different channels and provide the forum for the harmonisation of the value of transfers and targeting criteria | 1 | mid 2022 | PSNP Transfers Technical Committee | MoA FSCD, WFP | Scalable Safety Nets
| Revise Minimum Expenditure Basket to include food and non-food items, e.g. costs of water, health care, quality diet & strengthen monitoring of accessibility through the National Nutrition Information System (see 4.4. below) | 2 | end 2022 | PSNP Transfers Technical Committee | see 4.4. below | Scalable Safety Nets
| Consider improving quality of in-kind food parcels (slightly reducing quantity in order to improve quality if budget constraints) | 2 | end 2022 | PSNP Transfers Technical Committee | MoA FSCD, WFP | Scalable Safety Nets
2. Further assess the validity of using existing nutrition status data in early warning | EPHI led process to learn lessons from other countries and further assess validity of using nutrition status data in early warning |  | mid 2022 | NDRMC/MoH/EPHI |  | Health
2.1. Share experiences from other countries | Produce a short paper sharing experiences from other countries of using nutrition information in early warning as background for workshop (see below) | 1 | end Feb 2022 | EPHI | support from N4D? | Health
2.2. Technical workshop | Hold a technical workshop with nutritionists from Line Ministries & key development partners to (1) learn from experience in other African countries in using nutrition status data in early warning; (2) to further assess and discuss the validity of using existing nutrition status data in Ethiopia; (3) to explore ways of strengthening nutrition surveillance within the wider Ethiopian Nutrition Information System and linkages with the early warning system | 1 | March 2022 | ENCU | MoH, EPHI, NDRMC, MoA, UNICEF, WFP , others? | Health
2.3. Operational research | SAM and MAM validation (admissions and screening) for early warning & targeting through retrospective and real time analysis, to determine if they show seasonal, livelihood and shock related variations and changes in relation to past shocks | 1 | mid 2022 | EPHI | MoH, EPHI, NDRMC, MoA, UNICEF, WFP , others? | Health
| Analyse potential utility of MAM data for early warning/targeting & convergence with MAM MUAC based data for CU5 and PLW. This analysis should also determine the level of regional and woreda overlap with SAM admissions data | 1 | mid 2022 | MoH, EPHI, NDRMC, MoA, UNICEF, WFP , others? | MoH, EPHI, NDRMC, MoA, UNICEF, WFP , others? | Health
| Explore potential for collation and reporting of growth monitoring data (weight for age) at kebele and woreda level underpinned by analysis of coverage, data quality and quality of reporting as well as the potential role of digitalisation in data recording and reporting. | 2 | end 2022 | MoH | MoH, EPHI, NDRMC, MoA, UNICEF, WFP , others? | Health
3. Strengthening shock responsiveness & convergence of other sectoral programmes that are essential for nutrition | Support other sectors to strengthen shock responsive programmes converging on same nutritionally vulnerable populations | 1 | end 2022 | National Nutrition Coordination Body |  | Scalable Safety Nets
3.1. Strengthen the shock responsiveness of other sectoral programmes | Undertake an assessment of the shock responsiveness of different sectoral programmes, including convergence on areas most at risk of malnutrition & report to National Nutrition Coordination Body | 1 | mid 2022 | NNCB | National Nutrition Technical Committee | Scalable Safety Nets
| National Nutrition Coordination Body ensures different sectors strengthen shock responsiveness and convergence of programmes on nutritionally most at risk areas | 2 | end 2022 | NNCB | National Nutrition Technical Committee | Scalable Safety Nets
3.2. Promote coherence of humanitarian programmes with PSNP & other sectoral programmes | Support scale up of WFP voucher & other HRP financed programmes targeting PSNP households | 2 | end 2023 | NNCB | National Nutrition Technical Committee & Emergency Nutrition Cluster | Disaster Risk Management
4. Strengthen the National Nutrition Information System (NNIS) and links with Early Warning | Ensure that the Ethiopian Early Warning System is informed by a strengthened multi-sectoral National Nutrition Information System (NNIS) |  | end 2023 | National Nutrition Coordination Body |  | Scalable Safety Nets
IPC Acute Malnutrition protocols | Move ahead with piloting the IPC Acute Malnutrition Protocols within wider NNIS | 1 | mid 2022 | NNCB | National Nutrition Technical Committee & ENCU | Health
Strengthen monitoring of availability & accessibility of food and non-food needs (Minimum Expenditure Basket) to inform PSNP decisions on transfers modalities | Within the NNIS strengthen the monitoring of the availability and accessibility of food and non-food needs which influence nutrition through the NNIS | 1 | mid 2022 | NNCB | National Nutrition Technical Committee | Disaster Risk Management
Strengthen linkages between NNIS and EWS | Develop a service agreement between NNIS and Early Warning System outlining the data and analysis that will be provided to NDRMC to be used within early warning | 2 | end 2022 | NNCB & NDRMC | National Nutrition Technical Committee & ENCU | Scalable Safety Nets
Nutrition Information System guiding principles | Develop guiding principles for the NNIS and how it informs early warning | 2 | end 2022 | NNCB | National Nutrition Technical Committee | Scalable Safety Nets
Clarify analytical framework for National Nutrition Information System | Within UNISE clarify the analytical framework to be used for analysing the determinants of trends in malnutrition, including predicting & monitoring the impacts of shocks | 3 | end 2022 | NNCB | National Nutrition Technical Committee | Scalable Safety Nets
Explore options for sentinel site surveillance within NNIS | Consideration could be given to the establishment of sentinel site surveillance, through regular SMART surveys or longitudinal data collection), beginning with piloting in drought prone, i.e. PSNP, woredas to determine cost-effectiveness. Assess the feasibility of using academic institutions or Community Health Workers to undertake sentinel site surveillance. | 3 | end 2023 | NNCB | National Nutrition Technical Committee | Health
5. Promote high level political leadership to ensure multi-sectoral & inter-agency collaboration | Support Food and Nutrition Councils and technical bodies to to ensure multi-sectoral collaboration in Early Warning and shock-responsive programming |  | end 2022 | Prime Ministers Office |  | Health
5.1. Support the operationalisation of new national nutrition governance arrangements | Advocate for the implementation of new Food & Nutrition governance structures at federal and sub-national levels, including Food & Nutrition Councils & technical committees | 1 | mid 2022 | Prime Ministers Office | National Nutrition Technical Committee | Health
| Councils ensure sharing of information by sectors within NNIS and with Early Warning System as per service agreement (see 4.6. above) | 3 | end 2023 | National Food & Nutrition Council | National Nutrition Technical Committee | Health
| Councils ensure convergence of multi-sectoral shock responsive programes on most at risk | 3 | end 2023 | National Food & Nutrition Council | National Nutrition Technical Committee | Health